## Summary
CASA TOSALET · FF&E quantity forecast by phase
Order of magnitude on a non-final project. One phase per licence/building (order from 04/08/26 summary). Max = total + margin for tiered pricing. Change phases in Assumptions (col. E).
Indicator | Phase 1 · Casa Club | Phase 2 · Spa / Wellness | Phase 3 · Lodges A | Phase 4 · Lodges B | Total | Max to negotiate
Keys (rooms / lodges) | 14 | 18 | 12 | 12 | 56 | —
Bedrooms | 15 | 20 | 13 | 13 | 61 | —
Lounges (doubles with lounge + suites) | 4 | 6 | 3 | 3 | 16 | —
Accessible rooms (CTE DB-SUA) | 1 | 1 | 1 | 1 | 4 | —
F&B covers (indoor + terrace) | 190 | 70 | 40 | 60 | 360 | —
Group | Phase 1 · Casa Club | Phase 2 · Spa / Wellness | Phase 3 · Lodges A | Phase 4 · Lodges B | Total | Max to negotiate
Beds (90×200 bases) | 30 | 40 | 26 | 26 | 122 | 135
Mattresses | 30 | 40 | 26 | 26 | 122 | 135
Accessible-room kits | 1 | 1 | 1 | 1 | 4 | 5
Headboards | 15 | 20 | 13 | 13 | 61 | 68
Bedside tables | 30 | 40 | 26 | 26 | 122 | 135
Desks | 14 | 18 | 12 | 12 | 56 | 62
Desk & operator chairs | 16 | 20 | 14 | 14 | 64 | 71
Wardrobes | 15 | 20 | 13 | 13 | 61 | 68
Room lamps | 76 | 100 | 65 | 65 | 306 | 339
F&B lamps | 100 | 39 | 21 | 32 | 192 | 213
Common-area lamps | 40 | 2 | 2 | 2 | 46 | 52
Indoor dining chairs | 90 | 40 | 16 | 30 | 176 | 194
Terrace / outdoor chairs | 138 | 66 | 48 | 54 | 306 | 338
Common-area chairs | 28 | 0 | 80 | 0 | 108 | 120
Dining tables | 36 | 16 | 7 | 12 | 71 | 79
Outdoor tables | 54 | 30 | 22 | 24 | 130 | 144
Common-area tables | 3 | 0 | 12 | 0 | 15 | 19
Bar stools | 14 | 6 | 6 | 6 | 32 | 36
Armchairs & lounge seating | 86 | 62 | 33 | 41 | 222 | 248
Sofas | 7 | 6 | 3 | 3 | 19 | 22
Side & coffee tables | 78 | 38 | 15 | 19 | 150 | 167
Rugs | 19 | 26 | 16 | 16 | 77 | 86
Curtains (set per opening) | 42 | 54 | 36 | 36 | 168 | 185
Sunbeds & loungers | 80 | 31 | 24 | 24 | 159 | 176
Daybeds | 6 | 0 | 0 | 0 | 6 | 7
Parasols | 40 | 0 | 0 | 0 | 40 | 44
Reception desks | 1 | 1 | 1 | 1 | 4 | 5
Benches / luggage racks | 29 | 38 | 25 | 25 | 117 | 130
Mirrors | 14 | 18 | 12 | 12 | 56 | 62
Storage furniture | 4 | 6 | 3 | 3 | 16 | 18
In-room equipment | 42 | 54 | 36 | 36 | 168 | 186
Bathroom equipment | 15 | 20 | 13 | 13 | 61 | 68
Pool equipment | 2 | 1 | 0 | 0 | 3 | 4
Spa equipment | 0 | 12 | 0 | 0 | 12 | 14
High chairs | 6 | 2 | 2 | 2 | 12 | 14
Room textiles | 135 | 180 | 117 | 117 | 549 | 607
Bath textiles | 105 | 140 | 91 | 91 | 427 | 471
Total lamps (rooms + F&B + common areas) | 216 | 141 | 88 | 99 | 544 | 604
Total chairs (dining + terrace + common + desk) | 272 | 126 | 158 | 98 | 654 | 723

## Hotel Standards
Hotel-grade (contract) requirements to include in every supplier request
Research 18/10/2026. Legal status checked where a source was found; other lines are standard contract-furniture practice. Confirm with the architect, Turisme and the insurer before tendering.
Topic | Requirement / spec to request | Applies to | Legal status in Jávea (Comunitat Valenciana) | Source
Height-adjustable beds | Liftable bed bases (mechanical or electric) so housekeeping can work without bending; excludes extra/sofa beds in the Canarias law. | All hotel beds | NOT found as mandatory in the Comunitat Valenciana or at national level (checked 18/10/2026). Mandatory in Canarias (Ley 1/2026: 4–5* hotels 25% by 2027, 45% 2029, 75% 2031, 100% 2033); Baleares tourism law also requires it. Recommended anyway: likely to spread and a 2028 opening should not need retrofitting. | BOE-A-2026-17187 (Ley 1/2026 Canarias); idealista / mallorcadiario on Baleares
Upholstered seating — fire | Certificates UNE-EN 1021-1 (cigarette) and UNE-EN 1021-2 (match) for fabric + foam combination. | Restaurant, bar, lounge, library, multipurpose room seats; request for rooms too | Cited in CTE DB-SI, Section SI 1, para. 4 (upholstered fixed seats in assembly-type spaces). Request for all upholstery as contract standard. | CTE DB-SI Anejo G; SI 1 §4
Curtains and suspended textiles — fire | UNE-EN 13773 Class 1 (flame-retardant, inherently FR fabric preferred over treated fabric so it survives washing). | Public areas; request for rooms too | UNE-EN 13773 is cited in CTE DB-SI SI 1 §4 for suspended textiles in public-use areas. | CTE DB-SI Anejo G
Mattresses — fire | EN 597-1 / EN 597-2 (cigarette / match) contract mattresses; removable washable covers and protectors. | All beds | Contract standard; confirm with insurer/operator. | Industry practice (contract mattresses)
Accessible rooms | 1 accessible unit per establishment of 5–50 units: adapted bed height and clear space, wardrobe, desk, bathroom. | 4 rooms total (1 per licence) | Mandatory: CTE DB-SUA 9, Table 1.1. | CTE DB-SUA Section SUA 9
Durability — contract grade | Seating tested for non-domestic use (EN 16139), tables for non-domestic use (EN 15372); reinforced joints, replaceable parts, spare-part availability ≥ 5 years. | All loose furniture | Not a legal obligation; essential for hotel wear (domestic furniture fails fast). | Contract practice
Humidity and sea air | Moisture-stable woods, stainless/marine-grade fittings, UV-stable outdoor fabrics and solution-dyed acrylics; spa furniture rated for high humidity. | Outdoor, pool, spa furniture | Humidity named as a central design constraint (technical meeting 25/09/26). | #tosalet-comite-operativo 01/10/26
Hygiene and maintenance | Removable, washable covers; stain-resistant finishes; easy-clean leg/floor clearance for housekeeping; no fragile decorative parts in rooms. | Rooms, F&B | Operational standard. | Contract practice
5* classification (Decreto 10/2021) | Hotels are classified by a self-assessment questionnaire (5* = 650 points, Gran Lujo = 800). Room items count towards points: get the questionnaire Reyes already used (04/08/26) to check bed sizes and mandatory room equipment before ordering. | Hotels 1–2 (5*), 3–4 (4*) | Mandatory classification system; detailed room items not verified here. | turismecv.com webinar Decreto 10/2021

## Assumptions
CASA TOSALET · FF&E Quantity Forecast — Base Assumptions
Working version 18/10/2026 · project not yet final · indicative quantities to open supplier negotiations
Legend: BLUE text on yellow = editable assumptions (the whole file recalculates) · black = formulas · green = links to other sheets
Accommodation unit | Building / use | Category | Keys | Phase (1–4) | Indicative timing | Suites | Doubles with lounge | Doubles | Bedrooms | Lounges | Bathrooms | Lodge (1/0)
Hotel 1 · Casa Club | Main building: reception, members' restaurant, bar, bakery-café, library, privé, rooms | 5* | 14 | 1 | First licence · opening target 2028 (TBC) | 1 | 3 | 10 | 15 | 4 | 15 | 0
Hotel 2 · Spa / Wellness | Spa, gym, heated pool, wellness restaurant & bar, rooms | 5* | 18 | 2 | Spa by phases; hotel licence requested later (TBC) | 2 | 4 | 12 | 20 | 6 | 20 | 0
Hotel 3 · Lodges A (4*) | Glass-cube reception, healthy bar, lodges, multipurpose room | 4* | 12 | 3 | TBC | 1 | 2 | 9 | 13 | 3 | 13 | 1
Hotel 4 · Lodges B (4*) | Lodges, F&B outlet, own reception | 4* | 12 | 4 | TBC | 1 | 2 | 9 | 13 | 3 | 13 | 1
Total |  |  | 56 |  |  | 5 | 11 | 40 | 61 | 16 | 61
Parameters
% doubles with lounge | 20% | Assumption. Room types per hotel requested from Nacho (04/08/26); not yet received.
% suites | 10% | Assumption. Suite mandatory in 5* (min. 1 per 5* hotel, forced in the formula).
Bedrooms per suite | 2 | Suite = 2 bedrooms with bathroom + lounge.
Windows / openings per key (curtains) | 3 | Assumption, to be checked on the plans.
Negotiation margin (max quantity) | 10% | To request tiered min–max pricing from suppliers.
Covers per table (average) | 2.5 | Mix of 2- and 4-seat tables.
Calculation drivers per phase (used by the detail sheets)
Driver | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total
key | 14 | 18 | 12 | 12 | 56
bedroom | 15 | 20 | 13 | 13 | 61
lounge | 4 | 6 | 3 | 3 | 16
bathroom | 15 | 20 | 13 | 13 | 61
terrace | 14 | 18 | 12 | 12 | 56
window | 42 | 54 | 36 | 36 | 168
lodge | 0 | 0 | 12 | 12 | 24
hotel | 1 | 1 | 1 | 1 | 4
Note on E7: Phase order from the 04/08/26 summary: casa club first, then spa zone, then the two 4* hotels. Keys per hotel from casatosalet.com (14/18/12/12). Change the phase number to move a whole building.

## Rooms
Rooms and lodges — FF&E kit per unit, by phase
Quantity = qty per unit × driver per phase from Assumptions. Wardrobes and headboards may be bespoke joinery: check against the construction specification.
Item (EN) | Denominación (ES) — for suppliers | Summary group | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Max to negotiate | Notes / to confirm | Driver | Qty / unit
Height-adjustable (liftable) bed base 90×200 zip&link | Somier/base elevable 90×200 unible (zip & link) | Beds (90×200 bases) | 30 | 40 | 26 | 26 | 122 | 135 | 2 bases = 1 king, splits into twin. Liftable (mechanical or electric) for housekeeping ergonomics — mandatory in Canarias (Ley 1/2026); see Hotel Standards sheet. | bedroom | 2
Accessible-room furniture kit (bed, wardrobe, desk adapted) | Kit mobiliario habitación accesible | Accessible-room kits | 1 | 1 | 1 | 1 | 4 | 5 | CTE DB-SUA: 1 accessible unit per establishment of 5–50 units; 4 independent licences → 1 per hotel. Layout and heights to be fixed with the architect. | hotel | 1
Mattress 90×200 zip&link | Colchón 90×200 unible | Mattresses | 30 | 40 | 26 | 26 | 122 | 135 | Deep-sleep quality (MAVI / Passive House line). | bedroom | 2
Topper king 180×200 | Topper 180×200 | Room textiles | 15 | 20 | 13 | 13 | 61 | 68 |  | bedroom | 1
King headboard | Cabecero 180 | Headboards | 15 | 20 | 13 | 13 | 61 | 68 | Possibly bespoke joinery. | bedroom | 1
Bedside table | Mesita de noche | Bedside tables | 30 | 40 | 26 | 26 | 122 | 135 |  | bedroom | 2
Bedside lamp / reading wall light | Lámpara de mesita / aplique de lectura | Room lamps | 30 | 40 | 26 | 26 | 122 | 135 | Warm amber light, no blue (luz brasa concept). | bedroom | 2
Bed-end bench | Banqueta pie de cama | Benches / luggage racks | 15 | 20 | 13 | 13 | 61 | 68 |  | bedroom | 1
Bedroom armchair | Butaca dormitorio | Armchairs & lounge seating | 15 | 20 | 13 | 13 | 61 | 68 |  | bedroom | 1
Pouf / ottoman | Puf / otomana | Armchairs & lounge seating | 15 | 20 | 13 | 13 | 61 | 68 |  | bedroom | 1
Bedroom rug | Alfombra dormitorio | Rugs | 15 | 20 | 13 | 13 | 61 | 68 |  | bedroom | 1
Wardrobe (if not bespoke) | Armario (si no es a medida) | Wardrobes | 15 | 20 | 13 | 13 | 61 | 68 | CLARIFICATION: likely joinery within construction scope. | bedroom | 1
Desk / writing table | Escritorio | Desks | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Desk chair | Silla de escritorio | Desk & operator chairs | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Desk lamp | Lámpara de escritorio | Room lamps | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Bedroom floor lamp | Lámpara de pie dormitorio | Room lamps | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Decorative pendant / lamp | Lámpara colgante decorativa | Room lamps | 14 | 18 | 12 | 12 | 56 | 62 | Technical lighting is part of the architectural project, not FF&E. | key | 1
Side table | Mesa auxiliar | Side & coffee tables | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Full-length mirror | Espejo de cuerpo entero | Mirrors | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Luggage rack | Portamaletas | Benches / luggage racks | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Minibar | Minibar | In-room equipment | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Safe | Caja fuerte | In-room equipment | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Valet stand / coat rack | Galán de noche / perchero | In-room equipment | 14 | 18 | 12 | 12 | 56 | 62 |  | key | 1
Curtain + blackout (set per opening) | Cortina + blackout (juego por hueco) | Curtains (set per opening) | 42 | 54 | 36 | 36 | 168 | 185 | Openings to be taken from plans: assumed 3 per key. | window | 1
Lounge sofa (sofa bed) | Sofá (sofá cama) salón | Sofas | 4 | 6 | 3 | 3 | 16 | 18 | Only doubles with lounge and suites. | lounge | 1
Lounge coffee table | Mesa de centro salón | Side & coffee tables | 4 | 6 | 3 | 3 | 16 | 18 |  | lounge | 1
Lounge armchair | Butaca salón | Armchairs & lounge seating | 4 | 6 | 3 | 3 | 16 | 18 |  | lounge | 1
Lounge floor lamp | Lámpara de pie salón | Room lamps | 4 | 6 | 3 | 3 | 16 | 18 |  | lounge | 1
Lounge rug | Alfombra salón | Rugs | 4 | 6 | 3 | 3 | 16 | 18 |  | lounge | 1
Lounge console / TV unit | Consola / mueble salón | Storage furniture | 4 | 6 | 3 | 3 | 16 | 18 | CLARIFICATION: TV yes/no (silence doctrine). | lounge | 1
Terrace outdoor chair | Silla exterior terraza | Terrace / outdoor chairs | 28 | 36 | 24 | 24 | 112 | 124 |  | terrace | 2
Terrace outdoor table | Mesa exterior terraza | Outdoor tables | 14 | 18 | 12 | 12 | 56 | 62 |  | terrace | 1
Bathroom accessories (set) | Accesorios de baño (juego) | Bathroom equipment | 15 | 20 | 13 | 13 | 61 | 68 | Check whether included in the construction specification. | bathroom | 1
King sheet set (par 3) | Juego sábanas king (par 3) | Room textiles | 45 | 60 | 39 | 39 | 183 | 202 | OS&E: 3 changes par level. | bedroom | 3
King duvet | Edredón nórdico king | Room textiles | 15 | 20 | 13 | 13 | 61 | 68 |  | bedroom | 1
Bed pillows | Almohadas | Room textiles | 60 | 80 | 52 | 52 | 244 | 269 |  | bedroom | 4
Towel set (par 3) | Juego toallas (par 3) | Bath textiles | 45 | 60 | 39 | 39 | 183 | 202 |  | bathroom | 3
Bathrobe | Albornoz | Bath textiles | 60 | 80 | 52 | 52 | 244 | 269 | 2 guests × 2 changes. | bedroom | 4

## F&B
F&B outlets — covers and furniture, by phase
Covers NOT yet defined by the architect (requested 04/08/26). Blue values = assumptions; each hotel needs its own F&B point (meeting 12/08/26).
Outlet | Building | Phase (1–4) | Indoor covers | Terrace covers | Bar stools | Lounge seats | Indoor tables | Terrace tables | Table lamps (rechargeable) | Dining pendants | Lounge floor lamps | Lounge side tables | Children's high chairs
Members' restaurant | Casa Club | 1 | 70 | 50 | 0 | 0 | 28 | 20 | 48 | 14 | 0 | 0 | 2
Bar & lounge | Casa Club | 1 | 0 | 20 | 10 | 24 | 0 | 8 | 8 | 0 | 6 | 12 | 2
Bakery & café (open to the neighbourhood) | Casa Club | 1 | 20 | 30 | 4 | 0 | 8 | 12 | 20 | 4 | 0 | 0 | 2
Wellness restaurant | Spa / Wellness | 2 | 40 | 30 | 0 | 0 | 16 | 12 | 28 | 8 | 0 | 0 | 2
Wellness bar | Spa / Wellness | 2 | 0 | 0 | 6 | 12 | 0 | 0 | 0 | 0 | 3 | 6 | 0
Healthy bar | Lodges A | 3 | 16 | 24 | 6 | 0 | 7 | 10 | 17 | 4 | 0 | 0 | 2
Lodges F&B outlet | Lodges B | 4 | 30 | 30 | 6 | 8 | 12 | 12 | 24 | 6 | 2 | 4 | 2
Total |  |  | 176 | 184 | 32 | 44 | 71 | 74 | 145 | 36 | 11 | 22 | 12
Item (EN) | Denominación (ES) — for suppliers | Summary group | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Max to negotiate | Notes / to confirm | Source column
Indoor dining chair | Silla comedor interior | Indoor dining chairs | 90 | 40 | 16 | 30 | 176 | 194 |  | D
Terrace chair / armchair | Silla / butaca terraza | Terrace / outdoor chairs | 100 | 30 | 24 | 30 | 184 | 203 | Outdoor-grade material. | E
Bar stool | Taburete de barra | Bar stools | 14 | 6 | 6 | 6 | 32 | 36 |  | F
Lounge armchair / sofa (seats) | Butaca / sofá lounge (plazas) | Armchairs & lounge seating | 24 | 12 | 0 | 8 | 44 | 49 | Counted in seats. | G
Indoor dining table | Mesa comedor interior | Dining tables | 36 | 16 | 7 | 12 | 71 | 79 | Mix of 2 and 4 seats. | H
Terrace table | Mesa terraza | Outdoor tables | 40 | 12 | 10 | 12 | 74 | 82 |  | I
Rechargeable table lamp | Lámpara de mesa recargable | F&B lamps | 76 | 28 | 17 | 24 | 145 | 160 | 1 per table, indoor + terrace. | J
Decorative dining pendant | Lámpara colgante sala | F&B lamps | 18 | 8 | 4 | 6 | 36 | 40 | 1 every 2 indoor tables. | K
Lounge floor lamp | Lámpara de pie lounge | F&B lamps | 6 | 3 | 0 | 2 | 11 | 13 |  | L
Lounge side table | Mesa auxiliar lounge | Side & coffee tables | 12 | 6 | 0 | 4 | 22 | 25 |  | M
Children's high chair | Trona infantil | High chairs | 6 | 2 | 2 | 2 | 12 | 14 |  | N

## Pools & Spa
Pools, sun decks and spa — by phase
Website: three pools planned, one heated · 2,000 m² spa · ~30 simultaneous users (report 24/02/26). Sunbed numbers not yet defined by the architect.
Area | Phase (1–4) | Sunbeds | Daybeds | Parasols (1 per 2 sunbeds) | Side tables (1 per 2 sunbeds) | Towel stations
Main pool (swimming lane) | 1 | 50 | 4 | 25 | 25 | 1
Family pool | 1 | 30 | 2 | 15 | 15 | 1
Heated pool (wellness) | 2 | 16 | 0 | 0 | 8 | 1
Spa & lodges | Qty | Phase (1–4)
Sunbeds per lodge (private terrace) | 2 | per lodge
Spa relaxation loungers | 15 | 2
Treatment rooms | 6 | 2
Item (EN) | Denominación (ES) — for suppliers | Summary group | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Max to negotiate | Notes / to confirm
Pool sunbed | Tumbona piscina | Sunbeds & loungers | 80 | 16 | 0 | 0 | 96 | 106
Lodge terrace sunbed | Tumbona terraza lodge | Sunbeds & loungers | 0 | 0 | 24 | 24 | 48 | 53 | 2 per lodge.
Pool daybed | Daybed / cama balinesa | Daybeds | 6 | 0 | 0 | 0 | 6 | 7
Parasol | Sombrilla | Parasols | 40 | 0 | 0 | 0 | 40 | 44 | Not for the indoor pool.
Pool side table | Mesa auxiliar piscina | Side & coffee tables | 40 | 8 | 0 | 0 | 48 | 53
Towel station | Estación de toallas | Pool equipment | 2 | 1 | 0 | 0 | 3 | 4
Spa relaxation lounger | Tumbona relax spa | Sunbeds & loungers | 0 | 15 | 0 | 0 | 15 | 17 | Indoor, humidity-resistant materials.
Treatment bed | Camilla de tratamiento | Spa equipment | 0 | 6 | 0 | 0 | 6 | 7 | Often supplied by the spa operator.
Therapist stool | Taburete terapeuta | Spa equipment | 0 | 6 | 0 | 0 | 6 | 7
Note on B6: Pool locations not confirmed on the plans: change the phase if the family pool belongs to the lodges.
Note on B11: Assumption: ~50% of the spa's 30 simultaneous users.
Note on B12: CLARIFICATION: number of treatment rooms not defined (requested 04/08/26).

## Common Areas
Common areas — reception, library, privé, multipurpose room, by phase
Reception items repeat in every hotel (1 per licence, meeting 12/08/26). Library and privé in the casa club (meeting 26/05/26); multipurpose room in Lodges A (meeting 12/08/26).
Item (EN) | Denominación (ES) — for suppliers | Summary group | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Max to negotiate | Notes / to confirm | Phase (1–4) or 'per hotel' | Qty
Reception desk | Mostrador de recepción | Reception desks | 1 | 1 | 1 | 1 | 4 | 5 | 1 per hotel; Hotel 3 in glass cube. | per hotel | 1
Reception operator chair | Silla recepción | Desk & operator chairs | 2 | 2 | 2 | 2 | 8 | 9 |  | per hotel | 2
Reception waiting seats | Asientos espera recepción | Armchairs & lounge seating | 4 | 4 | 4 | 4 | 16 | 18 |  | per hotel | 4
Reception lamp | Lámpara recepción | Common-area lamps | 2 | 2 | 2 | 2 | 8 | 9 |  | per hotel | 2
Library / reading room armchair | Butaca biblioteca | Armchairs & lounge seating | 16 | 0 | 0 | 0 | 16 | 18 | Deep armchairs, natural light. | 1 | 16
Library sofa | Sofá biblioteca | Sofas | 3 | 0 | 0 | 0 | 3 | 4 |  | 1 | 3
Reading / work table | Mesa de lectura | Common-area tables | 2 | 0 | 0 | 0 | 2 | 3 | Quiet work, no fixed workstations. | 1 | 2
Reading table chair | Silla mesa de lectura | Common-area chairs | 12 | 0 | 0 | 0 | 12 | 14 |  | 1 | 12
Library side table | Mesa auxiliar biblioteca | Side & coffee tables | 8 | 0 | 0 | 0 | 8 | 9 |  | 1 | 8
Library reading lamp | Lámpara de lectura | Common-area lamps | 12 | 0 | 0 | 0 | 12 | 14 |  | 1 | 12
Privé / conference meeting table | Mesa de reuniones privé | Common-area tables | 1 | 0 | 0 | 0 | 1 | 2 | 16 seats. | 1 | 1
Privé meeting chair | Silla de reuniones | Common-area chairs | 16 | 0 | 0 | 0 | 16 | 18 | Book launches, intimate dinners, committees. | 1 | 16
Privé lounge seats | Asientos lounge privé | Armchairs & lounge seating | 8 | 0 | 0 | 0 | 8 | 9 |  | 1 | 8
Privé lamps | Lámparas privé | Common-area lamps | 6 | 0 | 0 | 0 | 6 | 7 |  | 1 | 6
Multipurpose room stacking chair | Silla apilable sala polivalente | Common-area chairs | 0 | 0 | 80 | 0 | 80 | 88 | Room divisible with panels, for corporate events. | 3 | 80
Multipurpose room folding table | Mesa plegable sala polivalente | Common-area tables | 0 | 0 | 12 | 0 | 12 | 14 |  | 3 | 12
Garden / outdoor lounge lamps | Lámparas exterior recargables | Common-area lamps | 20 | 0 | 0 | 0 | 20 | 22 | Amber light, gardens. | 1 | 20
Garden bench | Banco de jardín | Terrace / outdoor chairs | 10 | 0 | 0 | 0 | 10 | 11 |  | 1 | 10